**Project Roadmap & Detailed Schedule with Milestones**

**Timeline Overview: 24 Months (Sept 2025 – Aug 2027)**

**Key Milestones**

| **Phase** | **Key Milestone** | **Target Date** |
| --- | --- | --- |
| Phase 1: Inception & Kickoff | Stakeholder Workshop + Project Launch | 15 Sept 2025 |
| Phase 2: Curriculum Development | Final Curriculum & LMS Setup Complete | 20 Nov 2025 |
| Phase 3: Training Rollout Cohort 1 | 125 Participants Trained in 5 Countries | 15 Feb 2026 |
| Phase 4: Mid-Term Evaluation | MEL Report and Stakeholder Review | 30 Aug 2026 |
| Phase 5: Training Rollout Cohort 2 | Full 250+ Participants Trained | 30 April 2027 |
| Phase 6: Final Knowledge Sharing | Regional Symposium + Project Closeout | 15 Aug 2027 |

**Dependencies and Critical Path Highlights**

* Curriculum → LMS Deployment → ToT → Training Cohorts
* MEL setup → Midterm Review → Course Adaptation
* Procurement of ICT tools → LMS Launch → User Onboarding

**Note:** Gantt chart and PERT diagram available in editable formats (Excel or Project).